## Sheet1
Building X - Short Term Planning
|  |  | Project: |  | Building X
|  |  | Section / Area: |  | Ground Floor - Build A
|  |  | Owner(s): |  | Main Contractor
|  |  | Wk 1 of Lookahead: |  | 2026-01-05
[6 empty] | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01
| Activity | Resource Requirements | Make Ready Needs (Access / Plant / Interfaces / Design etc) | Planned & Actual % |  | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
1 | Area 1 - Set out sole plates | 2 operatives - Setting Out Team | Setting Information confirmed Construction Issue status | P | bar: 2026-01-05 to 2026-01-06
A
2 | Area 1 - Erect Studs and Sheet 1 side | 2 operatives - Squad A Sub A | BWIC to be issued and Damper setting out checked on first opening formed | P | bar: 2026-01-07 to 2026-01-09
A
3 | Area 1 - Review Damper Setting Out | Inspection |  | P | bar: 2026-01-08
A
4 | Area 1 - Sign Off 1st Fix Partition | Inspection |  | P | bar: 2026-01-09
A
5 | Area 1 - MEP contractor 1st Fix dwangs and electrical conduits | 2 operatives | Check 1:50 drawing latest setting out | P | bar: 2026-01-12 to 2026-01-14
A
6 | Area 1 - Sign Off MEP 1st Fix within Partitions | Inspection |  | P | bar: 2026-01-15
A
7 | Area 1 - 2nd Fix Boarding to Close Up Partitions | 2 Operatives - Squad A Sub A |  | P | bar: 2026-01-19 to 2026-01-21
A
8 | Area 1 - Inspection of Partitions | Inspection |  | P | bar: 2026-01-22
A
9 | Area 1 - Ames Tape Partitions | 2 operatives Sub A Sub B |  | P | bar: 2026-01-26 to 2026-01-29
A
10 | Area 2 - Set out sole plates | 2 operatives - Setting Out Team | Setting Information confirmed Construction Issue status | P | bar: 2026-01-07 to 2026-01-08
A
11 | Area 2 - Erect Studs and Sheet 1 side | 2 operatives - Squad A Sub A |  | P | bar: 2026-01-12 to 2026-01-14
A
12 | Area 2 - Sign Off 1st Fix Partition | Inspection |  | P | bar: 2026-01-15
A
13 | Area 2 - MEP contractor 1st Fix dwangs and electrical conduits | 2 operatives | Check 1:50 drawing latest setting out | P | bar: 2026-01-19 to 2026-01-21
A
14 | Area 2 - Sign Off MEP 1st Fix within Partitions | Inspection |  | P | bar: 2026-01-22
A
15 | Area 2 - 2nd Fix Boarding to Close Up Partitions | 2 Operatives - Squad A Sub A |  | P | bar: 2026-01-26 to 2026-01-28
A
16 | Area 2 - Commence Ames Taping | 2 Operatives - Squad A Sub B |  | P | bar: 2026-01-30
A
17 | Area 3 - Prepare concrete slab | 3 Operatives | Control of Dust to be reviewed | P | bar: 2026-01-12 to 2026-01-14
A
18 | Area 3 - Pump Screed | 4 Operatives | Ensure External Area is Segregated for Material Delivery and Pump Location | P | bar: 2026-01-15 to 2026-01-16; 2026-01-19
A
19 | Area 3 - Complete As Built Level Survey | Inspection | Engineer to be made available | P | bar: 2026-01-23
A
20 | Area 3 - Release Floor Plate to Dry Liner |  | Area Manager to Sign Off | P | bar: 2026-01-26
A
21 | Area 3 - Set out sole plates | 2 operatives - Setting Out Team | Setting Information confirmed Construction Issue status | P | bar: 2026-01-27 to 2026-01-28
A
22 | Area 3 - Erect Studs and Sheet 1 side | 2 operatives - Squad A Sub A |  | P | bar: 2026-01-29 to 2026-01-30
A
Week Commence
Week Commence
Week Commence
Repeat